# Project Charter: Data Center Consolidation and Migration Initiative

Project ID: MFH-DC-2024-001 | Version: 3.2 | Status: Approved

Sponsor: Michael Torres, Chief Information Officer | PM: James Thornton, Director of IT Infrastructure

Date: November 1, 2024 | Classification: For Internal Distribution

# 1. Project Overview

This charter authorizes the Data Center Consolidation and Migration Initiative for Meridian Financial Services. The project encompasses the strategic migration of all IT infrastructure from two aging on-premises data center facilities (Facility A in Newark, NJ and Facility B in Stamford, CT) to a hybrid colocation and cloud infrastructure model. The initiative is driven by expiring lease agreements, escalating operational costs, and the need to modernize infrastructure to support business growth targets over the next five years. The project will evaluate proposals from three shortlisted vendors: Vertex Colocation Partners (Vendor A), NovaBridge Solutions (Vendor B), and CloudScale IaaS (Vendor C), ultimately selecting and executing a migration to the optimal provider or combination thereof.

The current infrastructure comprises approximately 1,166 physical servers and 847 virtual machines distributed across 84 racks in two facilities. Annual operating costs exceed $4.12 million for facility leases alone, with total data center operating expenditure approaching $8.7 million annually when accounting for power, cooling, staff, and maintenance. The consolidation is projected to achieve a 25-35% reduction in total cost of ownership over a 3-year period while simultaneously improving infrastructure availability, security posture, and environmental sustainability.

## 1.1 Business Objectives

| ID | Objective | Description | Success Metric | Measurement |
| --- | --- | --- | --- | --- |
| OBJ-01 | Cost Reduction | Achieve minimum 25% TCO reduction over 3-year horizon | $14.2M 3-yr budget | Annual financial review |
| OBJ-02 | Availability | Improve infrastructure availability from 99.95% to 99.99% | < 52.6 min/yr downtime | Monthly SLA reporting |
| OBJ-03 | Risk Mitigation | Eliminate single points of failure in power and cooling | N+1 minimum all systems | Quarterly risk assessment |
| OBJ-04 | Compliance | Maintain SOC 2, PCI-DSS, HIPAA compliance through transition | Zero compliance gaps | Continuous monitoring |
| OBJ-05 | Sustainability | Reduce carbon footprint by 30% through PUE improvement | Target PUE < 1.50 | Quarterly emissions report |
| OBJ-06 | Scalability | Provide 50% growth capacity headroom post-migration | Available capacity tracking | Quarterly capacity review |
| OBJ-07 | DR Capability | Achieve RTO < 4 hours, RPO < 1 hour for Tier 1 workloads | DR test results | Semi-annual DR testing |
| OBJ-08 | Staff Efficiency | Reduce manual operational tasks by 40% through automation | Operational metrics | Monthly operations review |

# 2. Stakeholder Register

| Name | Title | Department | Project Role | Influence | Interest | Communication |
| --- | --- | --- | --- | --- | --- | --- |
| Michael Torres | CIO | Executive | Project Sponsor | High | High | Weekly status report |
| James Thornton | Director, IT Infrastructure | IT Operations | Project Manager | High | High | Daily standup |
| Sarah Chen | VP, Risk Management | Risk | Risk Oversight | High | Medium | Bi-weekly risk review |
| David Park | CISO | Security | Security Approval | High | High | Weekly security review |
| Rachel Kim | CFO | Finance | Budget Authority | High | Medium | Monthly financial review |
| Tom Bradley | VP, Application Development | Engineering | App Owner Rep | Medium | High | Weekly sync |
| Lisa Martinez | Director, Network Engineering | Network | Network Lead | Medium | High | Daily standup |
| Kevin Wong | Senior DBA | Database | Database Lead | Medium | High | Daily standup |
| Amanda Foster | Director, Compliance | Compliance | Compliance Advisor | High | Medium | Monthly review |
| Robert Chen | VP, Trading Operations | Trading | Business Stakeholder | High | High | Weekly impact review |
| Jennifer Adams | Director, Client Services | Client Ops | Business Stakeholder | Medium | Medium | Bi-weekly update |
| Mark Sullivan | Facilities Manager | Facilities | Physical Coordination | Low | High | As needed |
| Diana Patel | Procurement Manager | Procurement | Vendor Management | Medium | Medium | As needed |
| Steven Harris | Legal Counsel | Legal | Contract Review | High | Low | As needed |
| Catherine Brown | Internal Audit Director | Audit | Audit Oversight | Medium | Low | Quarterly audit |
| Alex Rodriguez | Change Manager | Change Mgmt | Change Control | Medium | High | CAB meetings |

# 3. RACI Matrix

R = Responsible (does the work), A = Accountable (owns the outcome), C = Consulted (provides input), I = Informed (kept updated)

| Activity | PM | Sponsor | Net Lead | DB Lead | Sec Lead | Compl. | Finance | App Lead | Facilities | Change Mgr |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vendor evaluation and selection | A | I | C | C | C | C | R | C | I | I |
| Contract negotiation | R | A | C | I | C | C | R | I | I | I |
| Network design (target state) | C | I | A | I | C | I | I | C | I | I |
| Migration wave planning | A | I | C | C | C | I | I | R | C | C |
| Pre-migration assessment | R | I | R | R | R | C | I | R | C | I |
| Pilot migration execution | A | I | R | R | C | I | I | R | C | R |
| Wave 1 migration (Tier 3) | A | I | R | C | C | I | I | R | R | R |
| Wave 2 migration (Tier 2) | A | I | R | R | C | I | I | R | R | R |
| Wave 3 migration (Tier 1) | A | A | R | R | R | C | I | R | R | R |
| Database migration | C | I | C | A | C | I | I | C | I | R |
| Security controls migration | C | I | C | I | A | C | I | I | I | R |
| Firewall rule migration | C | I | R | I | A | C | I | I | I | R |
| DNS cutover | C | I | A | I | C | I | I | C | I | R |
| Load balancer configuration | C | I | A | I | C | I | I | C | I | R |
| Storage migration | C | I | C | R | I | I | I | C | I | R |
| Backup system migration | C | I | C | R | C | I | I | C | I | R |
| Monitoring setup (target) | R | I | R | C | C | I | I | C | I | I |
| Performance validation | C | I | R | R | I | I | I | A | I | I |
| Compliance audit (pre-migration) | C | I | I | I | C | A | I | I | I | I |
| Compliance audit (post-migration) | C | I | I | I | C | A | I | I | I | I |
| Budget tracking and reporting | R | I | I | I | I | I | A | I | I | I |
| Change request processing | C | I | I | I | I | I | I | I | I | A |
| Stakeholder communications | A | C | I | I | I | I | I | I | I | I |
| Risk register maintenance | A | C | C | C | C | C | I | C | C | I |
| Issue escalation management | A | R | C | C | C | I | C | C | I | I |
| Physical decommissioning (Fac A) | C | I | C | I | I | I | C | I | A | R |
| Physical decommissioning (Fac B) | C | I | C | I | I | I | C | I | A | R |
| Lease termination coordination | C | A | I | I | I | I | C | I | R | I |
| Asset disposition | C | I | I | I | I | I | C | I | A | I |
| Knowledge transfer documentation | R | I | R | R | R | I | I | R | I | I |
| DR testing (pre-migration) | C | I | R | R | R | C | I | R | I | R |
| DR testing (post-migration) | C | I | R | R | R | C | I | R | I | R |
| Vendor SLA validation | A | I | R | I | C | C | I | R | I | I |
| Capacity planning (target) | R | I | C | C | I | I | C | C | I | I |
| License audit and transfer | R | I | I | C | I | I | C | C | I | I |
| Training and skill development | A | I | R | R | R | I | C | R | C | I |
| Post-migration optimization | A | I | R | R | C | I | C | R | I | I |
| Warranty claim coordination | R | I | C | I | I | I | C | I | R | I |
| Insurance policy update | C | I | I | I | I | I | A | I | C | I |
| Environmental monitoring setup | C | I | C | I | I | I | I | I | A | I |
| Circuit provisioning (new) | C | I | A | I | C | I | C | I | C | R |
| Circuit decommissioning (old) | C | I | A | I | I | I | C | I | C | R |
| Application dependency mapping | C | I | C | C | I | I | I | A | I | I |
| Runbook creation and validation | R | I | R | R | R | I | I | R | I | I |
| Go/No-Go decision (per wave) | C | A | C | C | C | C | C | C | C | R |
| Post-cutover hypercare | R | I | R | R | C | I | I | R | C | I |
| Lessons learned capture | A | C | C | C | C | I | I | C | I | C |
| Final project closeout | A | R | I | I | I | I | R | I | I | I |
| Quarterly business review setup | R | C | I | I | I | I | C | I | I | I |
| Vendor performance scoring | A | I | C | C | C | C | C | C | I | I |

# 4. Budget Breakdown

Total approved project budget: $14,200,000 over 36 months. The budget includes a 10% management reserve ($1,350,000) for unforeseen circumstances requiring Change Control Board approval for release.

| Phase | Description | Hardware/SW | Prof Services | Network/Circuits | Compliance | Contingency | Phase Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Phase 0 | Discovery and Assessment | $127,500 | $245,000 | $85,000 | $42,500 | $350,000 | $850,000 |
| Phase 1 | Foundation and Pilot Migration | $1,250,000 | $890,000 | $420,000 | $185,000 | $1,055,000 | $3,800,000 |
| Phase 2 | Wave 1-2 Migration (Tier 2-3) | $1,450,000 | $1,120,000 | $510,000 | $210,000 | $810,000 | $4,100,000 |
| Phase 3 | Wave 3 Migration (Tier 1) | $980,000 | $780,000 | $385,000 | $195,000 | $560,000 | $2,900,000 |
| Phase 4 | Optimization and Closeout | $320,000 | $285,000 | $195,000 | $95,000 | $305,000 | $1,200,000 |
|  | Management Reserve |  |  |  |  |  | $1,350,000 |
|  | TOTAL | $4,127,500 | $3,320,000 | $1,595,000 | $727,500 | $3,080,000 | $14,200,000 |

# 5. Risk Register

| Risk ID | Category | Description | Prob (1-5) | Impact (1-5) | Score | Strategy | Mitigation | Owner | Status | Trigger |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| RSK-001 | Schedule | Migration duration exceeds 18-month timeline | 3 | 4 | 12 | Mitigate | Buffer weeks in each wave; parallel workstreams | James Thornton | Open | Wave completion > 110% planned duration |
| RSK-002 | Technical | Application incompatibility in target environment | 3 | 5 | 15 | Mitigate | Pre-migration compatibility testing; rollback procedures | Tom Bradley | Open | Failed compatibility test |
| RSK-003 | Financial | Vendor cost escalation exceeds budget projections | 2 | 4 | 8 | Accept | Contract price locks; escalation cap clauses | Rachel Kim | Open | Annual cost review |
| RSK-004 | Compliance | Compliance gap during migration transition period | 3 | 5 | 15 | Mitigate | Parallel compliance controls; pre-migration audit | Amanda Foster | Open | Compliance control gap identified |
| RSK-005 | Security | Data breach during physical server transport | 1 | 5 | 5 | Transfer | Full-disk encryption; chain of custody; transit insurance | David Park | Open | Physical transport initiated |
| RSK-006 | Technical | Database migration causes data corruption | 2 | 5 | 10 | Mitigate | Checksum validation; parallel running; point-in-time recovery | Kevin Wong | Open | Pre-migration database snapshot |
| RSK-007 | Vendor | Selected vendor fails to meet SLA commitments | 2 | 4 | 8 | Mitigate | SLA penalties; quarterly reviews; exit clause at 12 months | James Thornton | Open | SLA breach reported |
| RSK-008 | Operational | Key staff attrition during migration project | 3 | 3 | 9 | Mitigate | Cross-training; retention bonuses; documented procedures | James Thornton | Open | Resignation notice received |
| RSK-009 | Technical | Network latency increase impacts trading platform | 2 | 5 | 10 | Mitigate | Pre-provisioned dedicated circuits; latency testing; rollback | Lisa Martinez | Open | Latency > 2ms measured |
| RSK-010 | Financial | Early lease termination penalties exceed estimates | 2 | 3 | 6 | Accept | Negotiate penalty reduction; offset with new vendor credits | Steven Harris | Open | Termination notice sent |
| RSK-011 | Technical | Live migration fails for high-memory VMs (dirty rate > BW) | 4 | 3 | 12 | Mitigate | Identify non-convergent VMs early; schedule warm migration | James Thornton | Open | Pre-migration assessment |
| RSK-012 | Vendor | NovaBridge early termination penalty dispute (0.35x vs 0.50x) | 2 | 4 | 8 | Mitigate | Legal review of contract terms; negotiate clarity before signing | Steven Harris | Open | Contract review meeting |
| RSK-013 | Technical | Storage I/O contention during concurrent migrations | 3 | 3 | 9 | Mitigate | Limit concurrent storage migrations; off-peak scheduling | Kevin Wong | Open | > 3 concurrent storage migrations |
| RSK-014 | Operational | DNS propagation delays cause client-facing outage | 2 | 4 | 8 | Mitigate | Low TTL pre-cutover; DNS monitoring; rollback DNS records | Lisa Martinez | Open | DNS cutover initiated |
| RSK-015 | Environmental | Hurricane/severe weather disrupts migration schedule | 1 | 4 | 4 | Accept | Seasonal planning; weather monitoring; flexible scheduling | Mark Sullivan | Open | Hurricane season (Jun-Nov) |
| RSK-016 | Compliance | PCI-DSS scope expansion during transition | 2 | 4 | 8 | Mitigate | Pre-migration PCI scope assessment; QSA consultation | Amanda Foster | Open | Scope change request |
| RSK-017 | Financial | Utility rate increases at existing facilities during transition | 3 | 2 | 6 | Accept | Budget contingency allocation; accelerate migration timeline | Rachel Kim | Open | Utility rate change notification |
| RSK-018 | Technical | Legacy application requires P2V conversion not tested | 3 | 3 | 9 | Mitigate | Identify all P2V candidates early; dedicated testing sprint | Tom Bradley | Open | P2V candidate identified |
| RSK-019 | Vendor | WAN circuit delivery delayed beyond 90-day lead time | 3 | 4 | 12 | Mitigate | Advance ordering; dual-carrier diversity; temporary connectivity | Lisa Martinez | Open | Circuit order placed |
| RSK-020 | Technical | Oracle licensing non-transferability to cloud/colo | 3 | 4 | 12 | Mitigate | License audit; Oracle rep engagement; BYOL assessment | James Thornton | Open | License audit initiated |
| RSK-021 | Security | Firewall rule migration introduces security gaps | 2 | 5 | 10 | Mitigate | Automated rule analysis; parallel firewall operation; pen test | David Park | Open | Rule migration started |
| RSK-022 | Operational | Monitoring gaps during transition period | 3 | 3 | 9 | Mitigate | Dual monitoring; agent deployment pre-cutover; alert validation | James Thornton | Open | Cutover window opened |
| RSK-023 | Technical | Jumbo frame (MTU 9000) not supported at target facility | 4 | 3 | 12 | Mitigate | Verify MTU support; test with MTU 1500; assess throughput impact | Lisa Martinez | Open | Vendor facility assessment |
| RSK-024 | Financial | Currency/market volatility impacts hardware procurement costs | 2 | 2 | 4 | Accept | Pre-negotiate pricing; bulk purchase agreements | Diana Patel | Open | Market review |
| RSK-025 | Vendor | Vendor staff turnover affects migration quality | 2 | 3 | 6 | Mitigate | Named resources in contract; knowledge transfer requirements | James Thornton | Open | Staff change notification |
| RSK-026 | Technical | Windows Server license true-up required post-migration | 3 | 3 | 9 | Mitigate | Pre-migration license inventory; Microsoft engagement | James Thornton | Open | License audit |
| RSK-027 | Compliance | HIPAA BAA renegotiation required with new provider | 2 | 3 | 6 | Mitigate | Early BAA negotiation; legal review of vendor BAA template | Amanda Foster | Open | Vendor selection |
| RSK-028 | Technical | Backup system incompatibility at target location | 2 | 4 | 8 | Mitigate | Backup solution assessment; migration or replacement planning | Kevin Wong | Open | Target environment assessment |
| RSK-029 | Operational | Knowledge loss if documentation is inadequate | 3 | 3 | 9 | Mitigate | Documentation sprints; peer review; runbook validation testing | James Thornton | Open | Pre-migration documentation review |
| RSK-030 | Technical | VM count discrepancy between systems (847 vs 831) | 2 | 2 | 4 | Investigate | Reconcile inventory across vCenter, CMDB, and asset management | James Thornton | Open | Inventory reconciliation |
| RSK-031 | Financial | TCO model sensitivity to power cost assumptions | 3 | 3 | 9 | Mitigate | Monte Carlo sensitivity analysis; multiple scenario planning | Rachel Kim | Open | Annual budget review |
| RSK-032 | Technical | CRAC-NWK-06 failure compromises cooling during migration | 3 | 4 | 12 | Mitigate | Expedite repair; portable cooling contingency; reduce load first | Mark Sullivan | Open | Summer peak load period |
| RSK-033 | Operational | Auto-renewal clause triggers if notice deadline missed | 4 | 4 | 16 | Mitigate | Calendar alerts for 90-day notice; legal tracking; backup plan | Steven Harris | Open | 90 days before expiry |
| RSK-034 | Technical | Facility A power readings conflict (1,847 kW vs 1,891 kW) | 2 | 2 | 4 | Investigate | Reconcile metering points; verify panel-level vs rack-level data | James Thornton | Open | Power audit review |
| RSK-035 | Vendor | Pricing discrepancy between proposal and comparison sheet | 3 | 3 | 9 | Investigate | Request written pricing confirmation; reference in contract | Diana Patel | Open | Final vendor negotiation |
| RSK-036 | Technical | UPS runtime at Facility B (8 min) below 10-min standard | 3 | 4 | 12 | Mitigate | Prioritize Facility B migration; portable UPS contingency | Mark Sullivan | Open | Pre-migration risk review |
| RSK-037 | Compliance | Gap in environmental monitoring during cutover windows | 2 | 3 | 6 | Mitigate | Portable environmental sensors; temporary monitoring scripts | Amanda Foster | Open | Cutover planning |
| RSK-038 | Technical | Generator fuel contamination at Facility A delays response | 2 | 4 | 8 | Mitigate | Immediate fuel polishing; biocide treatment; retest | Mark Sullivan | Open | Generator test failure |
| RSK-039 | Financial | Vendor B storage pricing discrepancy ($0.055 vs $0.062/GB) | 3 | 2 | 6 | Investigate | Request clarification from NovaBridge; confirm in writing | Diana Patel | Open | Contract negotiation |
| RSK-040 | Technical | Transfer switch ATS-A-02 degraded (340ms vs 10ms spec) | 3 | 4 | 12 | Mitigate | Expedite repair before migration; temporary bypass if needed | Mark Sullivan | Open | Power infrastructure review |

# 6. Milestone Schedule

| ID | Milestone | Target Date | Phase | Predecessor | Successor | Deliverable | Acceptance |
| --- | --- | --- | --- | --- | --- | --- | --- |
| M-01 | Project Kickoff | Nov 15, 2024 | Phase 0 | — | — | Charter signed, team mobilized | Sponsor sign-off |
| M-02 | Current State Assessment Complete | Dec 31, 2024 | Phase 0 | M-01 | M-03 | All assessments documented | PM approval |
| M-03 | Vendor Evaluation Complete | Jan 31, 2025 | Phase 0 | M-02 | M-04 | Vendor scorecard finalized | Steering committee |
| M-04 | Vendor Contract Executed | Feb 28, 2025 | Phase 0 | M-03 | M-05 | Signed contract | Legal + CIO approval |
| M-05 | Target Environment Ready | Apr 15, 2025 | Phase 1 | M-04 | M-06 | Circuits, cabs provisioned | Network + vendor sign-off |
| M-06 | Pilot Migration Complete | May 15, 2025 | Phase 1 | M-05 | M-07 | 2-3 non-prod VMs migrated | Performance validated |
| M-07 | Wave 1 Go/No-Go Decision | May 31, 2025 | Phase 2 | M-06 | M-08 | Pilot results reviewed | Steering committee |
| M-08 | Wave 1 Complete (Tier 3) | Jul 15, 2025 | Phase 2 | M-07 | M-09 | All Tier 3 workloads migrated | App owner sign-off |
| M-09 | Wave 2 Complete (Tier 2) | Sep 30, 2025 | Phase 2 | M-08 | M-10 | All Tier 2 workloads migrated | App owner sign-off |
| M-10 | Wave 3 Go/No-Go Decision | Oct 15, 2025 | Phase 3 | M-09 | M-11 | Wave 2 results reviewed | Steering committee |
| M-11 | Wave 3 Complete (Tier 1) | Dec 31, 2025 | Phase 3 | M-10 | M-12 | All Tier 1 workloads migrated | CIO + Risk sign-off |
| M-12 | Post-Migration Validation | Jan 31, 2026 | Phase 4 | M-11 | M-13 | All performance baselines met | QA sign-off |
| M-13 | Facility A Decommission | Feb 28, 2026 | Phase 4 | M-12 | M-14 | All equipment removed/disposed | Facilities sign-off |
| M-14 | Facility B Decommission | Mar 31, 2026 | Phase 4 | M-13 | M-15 | All equipment removed/disposed | Facilities sign-off |
| M-15 | Lease Termination (Both) | Apr 30, 2026 | Phase 4 | M-14 | M-16 | Lease termination confirmed | Legal sign-off |
| M-16 | Optimization Phase Complete | May 31, 2026 | Phase 4 | M-15 | M-17 | Cost optimization achieved | Financial review |
| M-17 | Project Closeout | Jun 30, 2026 | Phase 4 | M-16 | — | Final report delivered | Sponsor acceptance |
| M-18 | Facility B Lease Expiry Notice Deadline | Jul 1, 2026 | Contractual | — | — | 90-day notice for non-renewal | Legal calendar alert |
| M-19 | Facility B Lease Expiry | Sep 30, 2026 | Contractual | — | — | Lease term ends | Legal tracking |
| M-20 | Facility A Non-Renewal Notice Deadline | Dec 1, 2026 | Contractual | — | — | 90-day notice for non-renewal | Legal calendar alert |
| M-21 | Facility A Lease Expiry | Feb 28, 2027 | Contractual | — | — | Lease term ends | Legal tracking |
| M-22 | First Annual SLA Review | Feb 28, 2026 | Operational | M-04 | — | 12-month SLA performance review | Vendor + PM review |
| M-23 | Second Annual Budget Review | Nov 15, 2025 | Financial | — | — | Year 2 budget vs actual | CFO review |
| M-24 | DR Test (Post-Migration) | Mar 31, 2026 | Operational | M-12 | — | Full DR exercise at new site | Risk + CIO sign-off |
| M-25 | Compliance Re-Certification | Apr 30, 2026 | Compliance | M-12 | — | SOC 2 + PCI-DSS at new site | QSA + auditor |

# 7. Change Control Procedures

All changes to project scope, schedule, budget, or resource allocation must follow the change control process outlined below. The Change Control Board (CCB) meets every Tuesday at 14:00 ET to review pending change requests.

## 7.1 Change Request Classification

| Classification | Criteria | Approval Authority | Response SLA |
| --- | --- | --- | --- |
| Minor | < $10,000 budget impact; < 1 week schedule impact | Project Manager | 2 business days |
| Standard | $10,000 - $50,000 budget; 1-4 weeks schedule | CCB | 5 business days |
| Major | $50,000 - $200,000 budget; > 4 weeks schedule | CCB + Sponsor | 10 business days |
| Critical | > $200,000 budget; scope change; strategic impact | Steering Committee | Next scheduled meeting |

# 8. Communication Plan

| Communication | Audience | Owner | Frequency | Channel | Content |
| --- | --- | --- | --- | --- | --- |
| Daily standup | Project team | PM | Daily 09:30 ET | MS Teams | Status, blockers, plans |
| Weekly status report | Sponsor, stakeholders | PM | Friday 17:00 ET | Email + dashboard | Progress, risks, decisions needed |
| Bi-weekly risk review | Risk committee | PM + Risk | Alternate Tuesdays | In-person/Teams | Risk register review, mitigation status |
| Monthly steering committee | C-suite | PM + Sponsor | First Monday | In-person | Strategic review, budget, decisions |
| Quarterly business review | All stakeholders | PM | Quarter end | Presentation | Comprehensive review |
| Migration wave briefing | Impacted teams | PM + Wave lead | Pre-wave -2 weeks | Town hall | Scope, timeline, impact, support |
| Incident notification | All stakeholders | NOC + PM | Within 30 min | Email + SMS | Incident details, impact, ETA |
| Change notification | Impacted teams | Change Mgr | Per CCB schedule | Email + ticket | Change details, risk, rollback |
| Vendor performance review | PM, procurement | PM | Monthly | Meeting + report | SLA compliance, issues, improvements |
| Lessons learned session | Project team | PM | Post-wave | Workshop | What worked, what to improve |

# 9. Resource Plan

| Resource | Role | Type | Allocation | Phases | Duration | Responsibilities |
| --- | --- | --- | --- | --- | --- | --- |
| James Thornton | Project Manager | FTE | 100% | All phases | 36 months | Overall project delivery |
| Lisa Martinez | Network Lead | FTE | 75% | Phase 1-3 | 18 months | Network design and migration |
| Kevin Wong | Database Lead | FTE | 60% | Phase 2-3 | 12 months | Database migration |
| Tom Bradley | Application Lead | FTE | 50% | Phase 1-3 | 18 months | App compatibility and testing |
| David Park | Security Lead | FTE | 40% | All phases | 36 months | Security controls and compliance |
| Migration Engineer 1 | Infrastructure | Contract | 100% | Phase 1-3 | 15 months | Server migration execution |
| Migration Engineer 2 | Infrastructure | Contract | 100% | Phase 2-3 | 12 months | Server migration execution |
| Network Engineer | Network | Contract | 100% | Phase 1-3 | 15 months | Circuit provisioning, routing |
| Storage Engineer | Storage | Contract | 75% | Phase 2-3 | 12 months | SAN migration, replication |
| Test Engineer | QA | Contract | 100% | Phase 1-4 | 18 months | Performance testing, validation |

# Appendix A: Budget Visualization

# Appendix B: Risk Score Distribution

# Appendix C: Project Timeline

# Appendix D: Resource Plan

# Appendix A: Budget Allocation and Expenditure Forecast

The total approved capital budget for the consolidation program is $8.6M, with an additional $0.8M contingency reserve (9.3% of base budget). Colocation setup costs represent the largest single line item at $2.4M (27.9%), covering cabinet installation, power provisioning, structured cabling, and initial circuit provisioning across Vertex Colocation (primary) and NovaBridge (secondary/DR). Network circuit costs of $1.8M include dual 10G MPLS circuits, dark fiber cross-connects, and internet transit diversity. Through Q2 2025, actual spend is tracking 8.6% above plan ($2.37M actual vs. $2.20M planned), primarily due to expedited circuit provisioning fees from Lumen/Zayo and unanticipated asbestos remediation in the Newark facility cable trays.

# Appendix B: Risk Heat Map

Eight primary risks have been identified and assessed using the standard 5x5 risk framework. R-01 (Vendor Delay) is rated as the highest-priority risk due to the single-source dependency on Vertex Colocation for the primary migration wave build-out. Lead times for 100G cross-connects from Vertex have historically ranged from 6 to 12 weeks, which could impact the Wave 1 start date. R-05 (Compliance Gap) addresses the risk that SOC 2 Type II and PCI DSS 4.0 attestations for the target colocation facility may not be available before the Tier 1 workload migration, requiring a bridge audit and temporary compensating controls. R-03 (Budget Overrun) is positioned at high impact but lower probability, reflecting the contingency reserve allocation.

# Appendix C: Master Project Timeline

The consolidation program spans 60 weeks (approximately 15 months) from project kickoff to formal closure. Critical path items include the colocation build-out (weeks 8-20), which must complete before the pilot migration can begin, and the Wave 3 Tier 1 workload migration (weeks 36-46), which includes the core banking, trading, and risk engine applications. The current project status as of Week 12 shows the vendor selection phase completed on schedule, network design in progress, and the colocation build-out beginning. Key dependencies include: (1) Vertex Colocation cabinet readiness certification, (2) Lumen/Zayo circuit activation, and (3) firewall rule migration tool procurement from Tufin/AlgoSec.

# Appendix D: RACI Stakeholder Matrix

The RACI matrix defines responsibility assignments for ten key project activities across seven stakeholder groups. The CIO serves as the executive sponsor and is Accountable for vendor selection, budget approval, and the go-live decision. The VP of Infrastructure acts as the overall program manager and is Responsible for day-to-day execution. Network and Security teams share Responsible roles for their respective domains, with cross-consultation requirements built into the design review and migration planning phases. Application owners are designated as Consulted during wave execution to ensure workload-specific requirements and validation criteria are addressed. The Compliance Officer has dual Responsible assignments for the security review and compliance audit activities.

# 8. Change Management and Scheduling Constraints

8.1 Change Freeze Windows

The following scheduling constraints are mandated by Meridian Financial Services' Change Advisory Board (CAB) and must be incorporated into all migration wave planning. No production changes, including migrations, failovers, or infrastructure modifications, may be executed during the following periods:

| Window | Period | Duration | Rationale |
| --- | --- | --- | --- |
| Q1 End Freeze | March 25 – March 31 | 7 days | Fiscal quarter-end close processing |
| Q2 End Freeze | June 25 – June 30 | 6 days | Half-year financial reporting |
| Q3 End Freeze | September 25 – September 30 | 6 days | Fiscal quarter-end close processing |
| Year-End Freeze | December 15 – January 5 | 22 days | Annual audit, regulatory reporting, year-end settlements |
| Regulatory Window | January 2 – January 14 | 13 days | Annual regulatory filing period (SEC, FINRA) |
| Mid-Year Regulatory | July 1 – July 14 | 14 days | Semi-annual regulatory reporting (Basel III, stress tests) |
| Tax Reporting | April 1 – April 15 | 15 days | Corporate tax filing deadline processing |

Additionally, all production migrations must avoid the following recurring windows: Friday 16:00 through Monday 06:00 EST (weekend batch processing), the first and third Monday of each month (end-of-day settlement cycles), and any date within 48 hours of a Federal Reserve System maintenance window.

8.2 Migration Execution Windows

All migration wave cutover activities must be scheduled within approved execution windows: Tuesday through Thursday, 22:00–06:00 EST. Each execution window provides a maximum of 8 hours for cutover and validation. Waves requiring longer execution windows must receive CAB exemption approval with a minimum 15 business days' lead time.

# 9. Revised Budget Breakdown

Total approved project budget: $14,200,000 (approved by the Board of Directors on September 15, 2024). The budget is allocated across the following categories:

| Category | Allocated Amount | Notes |
| --- | --- | --- |
| Colocation Setup & Build-Out | $2,400,000 | Includes cage construction, power provisioning, cross-connects |
| Hardware Procurement | $3,200,000 | Servers, storage, networking equipment for new facility |
| Software Licensing | $1,150,000 | VMware, OS, backup, monitoring licenses |
| Migration Tooling & Services | $850,000 | Zerto, Carbonite, professional services |
| Network Infrastructure | $1,200,000 | WAN circuits, DDoS, firewall upgrades |
| Professional Services | $1,800,000 | Consultants, migration engineers, security assessment |
| Testing & Validation | $425,000 | Performance testing, DR testing, acceptance testing |
| Contingency (10%) | $1,200,000 | Risk buffer for unforeseen costs |
| Project Management | $350,000 | PMO staff, tools, reporting |
| Training & Documentation | $150,000 | Staff training, runbook updates, knowledge transfer |
| Decommissioning | $100,000 | Old facility teardown, data destruction, lease exit |
| TOTAL | $12,825,000 | Variance from approved budget: -$1,375,000 unallocated |

# 10. Updated RACI Matrix

| Activity | J. Thornton (PM) | R. Chen (Network) | K. Anderson (Storage) | P. Garcia (Migration) | M. Williams (Compliance) | T. Nakamura (Security) |
| --- | --- | --- | --- | --- | --- | --- |
| Migration Wave Planning | A | C | C | R | I | C |
| Network Cutover | I | R | I | A | I | C |
| Storage Migration | I | C | R | A | I | I |
| Security Assessment | I | C | I | I | C | R |
| Compliance Validation | I | I | I | I | R | A |
| Vendor Negotiation | R | C | C | I | C | I |
| DR Testing | A | C | R | C | I | C |
| Go/No-Go Decision | R | I | I | I | I | I |
| Post-Migration Audit | I | I | I | I | A | R |

Note: T. Nakamura (Sr. Security Architect) was added to the RACI matrix following the October 2024 security review. Resource allocation for this role is pending HR approval and has not yet been reflected in the staffing plan (Section 3.4).

# Appendix: Facility Compliance Assessment Report

Facility Compliance Assessment Report

Meridian Financial Services — Data Center Facilities A and B

Prepared by: Internal Audit and Compliance Division | Report Date: October 2024 | Assessment Period: September 1-30, 2024

## 1. Executive Summary

This report presents the findings of a comprehensive facility compliance assessment conducted across both Meridian Financial Services data center locations. The assessment evaluated physical security, environmental controls, power infrastructure, fire suppression systems, and regulatory compliance posture against SOC 2 Type II, ISO 27001, PCI-DSS Level 1, and HIPAA requirements. A total of 247 controls were evaluated, with 228 (92.3%) found fully compliant, 14 (5.7%) partially compliant requiring remediation, and 5 (2.0%) non-compliant requiring immediate attention. The five non-compliant findings include compromised cooling redundancy at Facility A (CRAC-NWK-06 failure), insufficient UPS battery runtime at Facility B (8 minutes vs. 10-minute minimum), overdue generator fuel maintenance, an expired fire suppression system inspection certificate, and incomplete visitor log retention.

## 2. Facility Specifications

### 2.1 Facility A — Newark, NJ

### 2.2 Facility B — Stamford, CT

## 3. Physical Security Controls Assessment

## 4. Power Infrastructure Compliance

## 5. Compliance Framework Mapping

The following table maps facility controls across four regulatory and industry frameworks. Each control is assessed for current compliance status with evidence references.

## 6. Remediation Roadmap

## Appendix A: Compliance Summary

## Appendix B: Remediation Cost Analysis

## Appendix C: Physical Security Assessment

| Attribute | Detail |
| --- | --- |
| Address | 1200 Technology Drive, Newark, NJ 07102 |
| Total Floor Space | 52,500 sq ft (40,000 raised floor + 12,500 support) |
| Building Type | Purpose-built data center, 2018 construction |
| Construction | Reinforced concrete, seismic zone compliance |
| Fire Rating | 2-hour fire-rated walls and floors |
| Raised Floor | 24-inch plenum, 250 lb/sq ft load rating |
| Ceiling Height | 12 ft under deck |
| Loading Dock | 2 bays, secured access, climate-controlled staging |
| Utility Provider | PSE&G (dual independent feeds) |
| Lessor | DataVault Properties LLC |
| Lease Expiry | February 28, 2027 (auto-renewal if notice not given 90 days prior) |

| Attribute | Detail |
| --- | --- |
| Address | 500 Harbor Point, Stamford, CT 06902 |
| Total Floor Space | 34,500 sq ft (28,000 raised floor + 6,500 support) |
| Building Type | Converted commercial space, 2015 retrofit |
| Construction | Steel frame with concrete deck |
| Fire Rating | 1-hour fire-rated (non-conformance noted for Tier III target) |
| Raised Floor | 18-inch plenum, 200 lb/sq ft load rating |
| Ceiling Height | 10 ft under deck (below standard 12 ft) |
| Loading Dock | 1 bay, exterior access only |
| Utility Provider | Eversource Energy (single feed) |
| Lessor | Metro Data Centers Inc. |
| Lease Expiry | May 31, 2026 (auto-renewal, 90-day notice required) |

| ID | Control | Current State (Fac A) | Target State | Status | Remediation |
| --- | --- | --- | --- | --- | --- |
| PS-01 | Perimeter fencing | 6ft chain-link + barbed wire | 8ft anti-climb with camera coverage | Partial | Upgrade fencing |
| PS-02 | Vehicle barriers | Concrete bollards at entrance | Anti-ram barriers, vehicle inspection | Compliant | — |
| PS-03 | Building access control | Card reader + PIN | Biometric + card + PIN (3-factor) | Partial | Add biometric |
| PS-04 | Mantrap entry | Installed, functional | Anti-piggybacking, weight sensors | Compliant | — |
| PS-05 | CCTV coverage | 42 cameras, 30-day retention | 100% coverage, 90-day retention | Partial | Increase retention |
| PS-06 | Guard service | 24/7 manned guard station | 24/7 manned with backup coverage | Compliant | — |
| PS-07 | Visitor management | Paper logbook | Electronic system with photo ID capture | Non-Compliant | Deploy electronic system |
| PS-08 | Data hall access | Card reader per zone | Biometric per zone, logged, alerting | Partial | Add biometric |
| PS-09 | Cabinet locks | Standard key locks | Electronic locks with audit trail | Partial | Upgrade to electronic |
| PS-10 | Loading dock security | CCTV + card access | Mantrap + CCTV + card + inspection area | Partial | Add mantrap |
| PS-11 | Emergency exits | Alarmed, CCTV monitored | Alarmed, CCTV, delayed egress | Compliant | — |
| PS-12 | Lighting | Interior: adequate; Exterior: partial | Full perimeter lighting, motion-activated | Partial | Improve exterior |
| PS-13 | Intrusion detection | Door sensors + motion in halls | Comprehensive IDS, glass break, vibration | Partial | Add vibration sensors |
| PS-14 | Key management | Physical key cabinet, log | Electronic key management system | Partial | Deploy key mgmt system |
| PS-15 | Background checks | Pre-employment criminal check | Criminal + credit + reference check | Compliant | — |
| PS-16 | Security awareness training | Annual online training | Annual + quarterly refresher | Partial | Add quarterly sessions |
| PS-17 | Incident response plan | Documented, tested annually | Documented, tested semi-annually | Compliant | — |
| PS-18 | Asset tagging | Barcode labels on servers | RFID tags on all IT assets | Partial | Deploy RFID |
| PS-19 | Waste disposal | Locked bins, monthly pickup | Certified NAID AAA destruction | Compliant | — |
| PS-20 | Clean desk policy | Informal enforcement | Policy documented, audited monthly | Partial | Document and audit |

| Unit | Model | Test Date | Test Type | Result | Notes |
| --- | --- | --- | --- | --- | --- |
| UPS-A-01 | Eaton 93PM | 2024-03-15 | Load bank test | PASS | 12 min runtime at full load |
| UPS-A-02 | Eaton 93PM | 2024-03-15 | Load bank test | PASS | 12 min runtime at full load |
| UPS-A-03 | Eaton 93PM | 2024-06-22 | Load bank test | PASS | 14 min runtime at full load |
| UPS-A-04 | Eaton 93PM | 2024-06-22 | Load bank test | PASS | 13 min runtime at full load |
| UPS-B-01 | Vertiv EXL | 2024-04-18 | Load bank test | WARNING | 8 min runtime (below 10-min minimum) |
| UPS-B-02 | Vertiv EXL | 2024-04-18 | Functional test | PASS | Standby unit, transfer verified |

| Unit | Model | Test Date | Test Type | Result | Notes |
| --- | --- | --- | --- | --- | --- |
| GEN-A-01 | CAT C32 | 2024-05-10 | Load test (2hr) | PASS | Transfer time: 8.2s. Fuel polishing OVERDUE |
| GEN-A-02 | CAT C32 | 2024-05-10 | Load test (2hr) | PASS | Transfer time: 7.8s. Normal operation |
| GEN-B-01 | Cummins QSK60 | 2024-07-15 | Load test (2hr) | PASS | Transfer time: 9.1s |
| GEN-B-02 | Cummins QSK60 | 2024-07-15 | Load test (1hr) | PASS | Scheduled maintenance up to date |

| Control ID | Description | SOC 2 | ISO 27001 | PCI-DSS | HIPAA | Status | Evidence Ref |
| --- | --- | --- | --- | --- | --- | --- | --- |
| CTRL-001 | Physical access policy | CC6.1 | A.11.1.1 | 9.1 | 164.310(a)(1) | Compliant | POL-SEC-001 |
| CTRL-002 | Access authorization process | CC6.1 | A.11.1.2 | 9.2 | 164.310(a)(2) | Compliant | PRO-SEC-002 |
| CTRL-003 | Visitor escort procedures | CC6.2 | A.11.1.6 | 9.4.1 | 164.310(a)(2) | Compliant | PRO-SEC-003 |
| CTRL-004 | Access revocation | CC6.3 | A.9.2.6 | 9.3 | 164.312(a)(2) | Compliant | PRO-HR-001 |
| CTRL-005 | CCTV monitoring | CC6.1 | A.11.1.1 | 9.1.1 | — | Partial | RPT-CCTV-Q3 |
| CTRL-006 | Environmental monitoring | CC6.4 | A.11.2.2 | 9.1 | 164.310(a)(2) | Compliant | SYS-ENVMON |
| CTRL-007 | Fire detection | CC6.4 | A.11.1.4 | 9.1 | — | Compliant | RPT-FIRE-2024 |
| CTRL-008 | Fire suppression | CC6.4 | A.11.1.4 | 9.1 | — | Non-Compliant | RPT-FIRE-2024 (expired cert) |
| CTRL-009 | Water detection | CC6.4 | A.11.2.1 | — | — | Compliant | SYS-WLEAK |
| CTRL-010 | UPS systems | CC6.4 | A.11.2.2 | 9.1 | 164.310(a)(2) | Partial | RPT-UPS-2024 (Fac B 8min) |
| CTRL-011 | Generator systems | CC6.4 | A.11.2.2 | 9.1 | 164.310(a)(2) | Compliant | DOC-SYS-861 |
| CTRL-012 | Power redundancy | CC6.4 | A.11.2.2 | 9.1 | — | Compliant | DOC-PRO-820 |
| CTRL-013 | Cooling redundancy | CC6.4 | A.11.2.2 | 9.1 | — | Compliant | DOC-PRO-901 |
| CTRL-014 | Rack security | CC6.1 | A.11.2.1 | 9.1 | — | Compliant | DOC-RPT-313 |
| CTRL-015 | Cable management | CC6.4 | A.11.2.3 | — | — | Partial | DOC-AUD-848 |
| CTRL-016 | Raised floor maintenance | CC6.4 | A.11.2.4 | — | — | Compliant | DOC-AUD-815 |
| CTRL-017 | Equipment labeling | CC6.5 | A.8.1.1 | 9.7.1 | — | Compliant | DOC-SYS-116 |
| CTRL-018 | Asset inventory | CC6.5 | A.8.1.1 | 9.7.1 | 164.310(d)(1) | Compliant | DOC-POL-150 |
| CTRL-019 | Media destruction | CC6.5 | A.8.3.2 | 9.8.1 | 164.310(d)(2) | Compliant | DOC-RPT-675 |
| CTRL-020 | Backup power testing | CC6.4 | A.11.2.2 | — | — | Compliant | DOC-PRO-774 |
| CTRL-021 | Emergency procedures | CC6.6 | A.11.1.4 | 12.10 | 164.308(a)(7) | Compliant | DOC-RPT-960 |
| CTRL-022 | Business continuity | CC6.6 | A.17.1.1 | 12.10.1 | 164.308(a)(7) | Partial | DOC-SYS-451 |
| CTRL-023 | Disaster recovery plan | CC6.6 | A.17.1.2 | — | 164.308(a)(7) | Compliant | DOC-PRO-684 |
| CTRL-024 | DR testing | CC6.6 | A.17.2.1 | — | 164.308(a)(7) | Compliant | DOC-SYS-340 |
| CTRL-025 | Incident response plan | CC6.6 | A.16.1.1 | 12.10 | 164.308(a)(6) | Compliant | DOC-AUD-113 |
| CTRL-026 | Incident notification | CC6.6 | A.16.1.2 | 12.10 | 164.308(a)(6) | Non-Compliant | DOC-SYS-437 |
| CTRL-027 | Risk assessment | CC3.1 | A.8.2.1 | 12.2 | 164.308(a)(1) | Compliant | DOC-AUD-703 |
| CTRL-028 | Vulnerability management | CC7.1 | A.12.6.1 | 11.2 | — | Compliant | DOC-SYS-591 |
| CTRL-029 | Patch management | CC7.1 | A.12.6.1 | 6.2 | — | Compliant | DOC-AUD-873 |
| CTRL-030 | Change management | CC8.1 | A.12.1.2 | 6.4 | 164.312(e)(2) | Compliant | DOC-PRO-530 |
| CTRL-031 | Configuration baseline | CC8.1 | A.12.5.1 | 2.2 | — | Partial | DOC-SYS-242 |
| CTRL-032 | Log management | CC7.2 | A.12.4.1 | 10.1 | 164.312(b) | Compliant | DOC-AUD-641 |
| CTRL-033 | Log retention | CC7.2 | A.12.4.3 | 10.7 | — | Compliant | DOC-PRO-195 |
| CTRL-034 | Network segmentation | CC6.1 | A.13.1.1 | 1.2 | 164.312(e)(1) | Compliant | DOC-PRO-773 |
| CTRL-035 | Firewall rules review | CC6.1 | A.13.1.1 | 1.1.7 | — | Compliant | DOC-AUD-109 |
| CTRL-036 | Intrusion detection | CC7.1 | A.13.1.1 | 11.4 | — | Compliant | DOC-AUD-510 |
| CTRL-037 | Encryption at rest | CC6.7 | A.10.1.1 | 3.4 | 164.312(a)(2) | Compliant | DOC-RPT-283 |
| CTRL-038 | Encryption in transit | CC6.7 | A.10.1.1 | 4.1 | 164.312(e)(1) | Partial | DOC-SYS-628 |
| CTRL-039 | Key management | CC6.7 | A.10.1.2 | 3.5 | — | Compliant | DOC-PRO-388 |
| CTRL-040 | Anti-malware | CC7.1 | A.12.2.1 | 5.1 | — | Compliant | DOC-AUD-846 |
| CTRL-041 | Security awareness | CC1.4 | A.7.2.2 | 12.6 | 164.308(a)(5) | Compliant | DOC-AUD-641 |
| CTRL-042 | Background checks | CC1.4 | A.7.1.1 | 12.7 | 164.308(a)(3) | Non-Compliant | DOC-AUD-451 |
| CTRL-043 | Vendor risk assessment | CC9.2 | A.15.1.1 | 12.8 | 164.308(b)(1) | Compliant | DOC-RPT-265 |
| CTRL-044 | Vendor due diligence | CC9.2 | A.15.1.2 | 12.8.2 | 164.308(b)(1) | Compliant | DOC-AUD-389 |
| CTRL-045 | Data classification | CC6.5 | A.8.2.1 | 3.1 | 164.312(a)(1) | Compliant | DOC-PRO-160 |
| CTRL-046 | Data retention policy | CC6.5 | A.8.2.3 | 3.1 | 164.530(j) | Compliant | DOC-AUD-769 |
| CTRL-047 | Privacy controls | CC6.5 | A.18.1.4 | — | 164.530(c) | Partial | DOC-SYS-180 |
| CTRL-048 | Audit trail | CC7.2 | A.12.4.1 | 10.2 | 164.312(b) | Compliant | DOC-RPT-759 |
| CTRL-049 | Segregation of duties | CC6.3 | A.6.1.2 | 7.1 | 164.312(a)(1) | Compliant | DOC-RPT-298 |
| CTRL-050 | Password policy | CC6.1 | A.9.4.3 | 8.2.3 | 164.312(d) | Compliant | DOC-SYS-589 |
| CTRL-051 | Multi-factor auth | CC6.1 | A.9.4.2 | 8.3 | 164.312(d) | Compliant | DOC-SYS-821 |
| CTRL-052 | Session management | CC6.1 | A.9.4.2 | 8.1.8 | — | Compliant | DOC-AUD-162 |
| CTRL-053 | Remote access | CC6.1 | A.9.4.2 | 1.3.5 | 164.312(e)(1) | Compliant | DOC-SYS-713 |
| CTRL-054 | Wireless security | CC6.1 | A.13.1.1 | 1.2.3 | — | Partial | DOC-SYS-852 |
| CTRL-055 | Physical media transport | CC6.5 | A.8.3.3 | 9.6 | 164.310(d)(1) | Compliant | DOC-POL-217 |
| CTRL-056 | Decommissioning | CC6.5 | A.11.2.7 | 9.8 | 164.310(d)(2) | Compliant | DOC-SYS-329 |
| CTRL-057 | Capacity management | CC6.4 | A.12.1.3 | — | — | Compliant | DOC-POL-476 |
| CTRL-058 | Performance monitoring | CC7.2 | A.12.1.3 | — | — | Non-Compliant | DOC-AUD-115 |
| CTRL-059 | Availability monitoring | CC7.2 | A.12.1.3 | — | — | Compliant | DOC-PRO-845 |
| CTRL-060 | Backup procedures | CC6.6 | A.12.3.1 | — | 164.308(a)(7) | Compliant | DOC-PRO-436 |
| CTRL-061 | Backup testing | CC6.6 | A.12.3.1 | — | 164.308(a)(7) | Compliant | DOC-AUD-249 |
| CTRL-062 | Restoration testing | CC6.6 | A.17.2.1 | — | 164.308(a)(7) | Compliant | DOC-SYS-424 |
| CTRL-063 | Legal compliance | CC1.1 | A.18.1.1 | 12.1 | 164.530(i) | Partial | DOC-POL-379 |
| CTRL-064 | Regulatory monitoring | CC1.1 | A.18.1.1 | 12.1 | — | Compliant | DOC-RPT-802 |
| CTRL-065 | Internal audit | CC4.1 | A.18.2.1 | 12.11 | 164.308(a)(8) | Compliant | DOC-AUD-784 |
| CTRL-066 | External audit | CC4.1 | A.18.2.1 | 11.3 | — | Compliant | DOC-RPT-995 |
| CTRL-067 | Penetration testing | CC7.1 | A.18.2.3 | 11.3 | — | Compliant | DOC-AUD-531 |
| CTRL-068 | Insurance coverage | CC9.1 | A.15.1.1 | — | — | Compliant | DOC-PRO-838 |
| CTRL-069 | Contractual obligations | CC9.1 | A.15.1.2 | 12.8 | 164.308(b)(1) | Compliant | DOC-PRO-999 |
| CTRL-070 | Service level agreements | CC9.1 | A.15.2.1 | — | — | Partial | DOC-RPT-494 |
| CTRL-071 | Subcontractor controls | CC9.2 | A.15.2.2 | 12.8.2 | 164.308(b)(1) | Compliant | DOC-AUD-769 |
| CTRL-072 | Intellectual property | CC6.5 | A.18.1.2 | — | — | Compliant | DOC-AUD-105 |
| CTRL-073 | Records management | CC6.5 | A.8.2.3 | 10.7 | 164.530(j) | Compliant | DOC-PRO-860 |
| CTRL-074 | Notification procedures | CC6.6 | A.16.1.2 | 12.10.5 | 164.308(a)(6) | Non-Compliant | DOC-POL-803 |
| CTRL-075 | Escalation procedures | CC6.6 | A.16.1.2 | 12.10.4 | — | Compliant | DOC-POL-338 |
| CTRL-076 | Root cause analysis | CC6.6 | A.16.1.6 | 12.10.6 | — | Compliant | DOC-PRO-840 |
| CTRL-077 | Lessons learned | CC6.6 | A.16.1.6 | — | — | Compliant | DOC-PRO-456 |
| CTRL-078 | Emergency lighting | CC6.4 | A.11.1.4 | 9.1 | — | Compliant | DOC-POL-842 |
| CTRL-079 | HVAC maintenance | CC6.4 | A.11.2.4 | — | — | Partial | DOC-PRO-913 |
| CTRL-080 | Humidity control | CC6.4 | A.11.2.2 | — | — | Compliant | DOC-SYS-670 |

| ID | Action | Priority | Target Date | Est. Cost | Category | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| REM-001 | CRAC-NWK-06 repair/replacement | High | Q4 2024 | $45,000 | Cooling | Mark Sullivan |
| REM-002 | UPS-B battery upgrade to 10+ min runtime | High | Q4 2024 | $125,000 | Power | Mark Sullivan |
| REM-003 | Generator fuel polishing (GEN-A-01) | High | Immediate | $4,200 | Power | Mark Sullivan |
| REM-004 | Fire suppression inspection recertification | High | Q4 2024 | $8,500 | Safety | Mark Sullivan |
| REM-005 | Electronic visitor management system | Medium | Q1 2025 | $15,000 | Security | David Park |
| REM-006 | Biometric access control deployment | Medium | Q1 2025 | $85,000 | Security | David Park |
| REM-007 | CCTV retention increase to 90 days | Medium | Q1 2025 | $12,000 | Security | David Park |
| REM-008 | Electronic cabinet locks with audit trail | Medium | Q2 2025 | $42,000 | Security | David Park |
| REM-009 | RFID asset tagging deployment | Low | Q2 2025 | $28,000 | Asset Mgmt | James Thornton |
| REM-010 | Perimeter fencing upgrade | Low | Q2 2025 | $35,000 | Physical | Mark Sullivan |
| REM-011 | ATS-A-02 repair (340ms transfer time) | High | Q4 2024 | $18,000 | Power | Mark Sullivan |
| REM-012 | EPO system testing at Facility B | Medium | Q4 2024 | $2,000 | Safety | Mark Sullivan |

# Appendix: Disaster Recovery Runbook

Disaster Recovery and Business Continuity Runbook

Meridian Financial Services — Infrastructure Operations Division

Document ID: DR-RUN-2024-007 | Version: 4.1 | Last Updated: October 2024

Document Owner: Michael Torres, CIO | Reviewed By: Sarah Chen, VP Operations

## Table of Contents

1. Purpose and Scope

2. Recovery Objectives by Workload Tier

3. Failover Procedures — Tier 1 (Mission Critical)

4. Failover Procedures — Tier 2 (Business Essential)

5. Failover Procedures — Tier 3 (Standard Operations)

6. Failover Procedures — Tier 4 (Development/Test)

7. Communication and Escalation Plan

8. DR Test Results and History

9. Dependency Chain Analysis

10. Recovery Site Specifications

11. Data Replication Architecture

Appendix A: Contact Directory

Appendix B: Recovery Validation Checklists

Appendix C: Regulatory Requirements for DR

## 1. Purpose and Scope

This runbook defines the disaster recovery (DR) and business continuity procedures for all production workloads hosted across Meridian Financial Services' two data center facilities. The document covers failover initiation criteria, execution procedures, communication protocols, and validation steps for each workload tier.

Scope: All production workloads classified as Tier 1 through Tier 4, encompassing 55 primary workloads, 200 virtual machines, and 38 storage arrays across Facility A (Newark, NJ) and Facility B (Stamford, CT). This runbook does NOT cover development or sandbox environments unless they are classified as Tier 4 with formal SLA requirements.

Regulatory context: As a financial services firm, Meridian is subject to FINRA Rule 4370 (Business Continuity Plans), SEC Rule 17a-4 (Records Retention), and OCC Bulletin 2019-58 (Third-Party Relationships). The DR program must demonstrate annual testing and documented recovery within stated RTO/RPO targets.

## 2. Recovery Objectives by Workload Tier

The following table defines the recovery time objective (RTO) and recovery point objective (RPO) for each workload tier. These targets were established by the Business Continuity Committee in September 2024 and approved by the Board of Directors.

Note: The RTO and RPO targets in this document supersede any previously documented targets in operational handbooks or workload configuration sheets. The September 2024 Board resolution formally adopted these targets effective October 1, 2024.

## 3. Failover Procedures — Tier 1 (Mission Critical)

### 3.1 Initiation Criteria

Tier 1 failover is initiated when ANY of the following conditions are met:
• Primary facility declares a P1 outage affecting compute or storage
• Network connectivity to primary facility is lost for >5 minutes
• Environmental conditions exceed ASHRAE A1 envelope (>35°C inlet)
• Utility power failure with UPS runtime below 15 minutes
• Declared regional emergency (natural disaster, civil unrest)

### 3.2 Execution Steps

1. DR Coordinator confirms outage severity with NOC (5 min)

2. Notify CIO and VP Operations via emergency channel (5 min)

3. Activate Zerto failover group for Tier 1 VPGs (10 min)

4. Verify storage replication checkpoint consistency (5 min)

5. Update DNS records for Tier 1 services (3 min, automated)

6. Validate network connectivity to DR site (5 min)

7. Execute application health checks per validation checklist (15 min)

8. Confirm trading system connectivity to exchange gateways (10 min)

9. Verify database consistency across replicated nodes (15 min)

10. Notify business unit leaders of activation status (5 min)

11. Update monitoring thresholds for DR environment (5 min)

12. Begin continuous availability monitoring (ongoing)

### 3.3 Failover Sequence Dependencies

The following dependency chain must be respected during Tier 1 failover. Services must be activated in the specified order to prevent cascading failures:

## 4. Failover Procedures — Tier 2 (Business Essential)

### 4.1 Initiation Criteria

Tier 2 failover is initiated when:
• Primary facility P1 outage exceeds 30 minutes
• Tier 1 failover has been executed and dependent Tier 2 workloads require activation
• Application-level monitoring detects sustained error rate >5% for >15 minutes

### 4.2 Execution Steps

1. Confirm Tier 1 failover completion status (5 min)

2. Activate Tier 2 Zerto VPGs (15 min)

3. Update application configuration for DR endpoints (10 min)

4. Execute dependency validation against Tier 1 services (10 min)

5. Run compliance system integrity checks (20 min)

6. Verify client-facing portal accessibility (10 min)

7. Test risk analytics data feed connectivity (15 min)

8. Notify affected business units (10 min)

## 5. Failover Procedures — Tier 3 (Standard Operations)

### 5.1 Initiation Criteria

Tier 3 failover is initiated when:
• Extended outage declared (>4 hours projected duration)
• Primary facility declared non-operational for >24 hours
• Regulatory requirement for continued reporting operations

### 5.2 Execution Steps

1. Assess extended outage duration estimate (30 min)

2. Restore from latest asynchronous snapshot (60-120 min)

3. Apply transaction logs to minimize data loss (30-60 min)

4. Validate reporting database integrity (30 min)

5. Restart batch processing jobs from last checkpoint (45 min)

6. Verify regulatory reporting pipeline (20 min)

## 6. Failover Procedures — Tier 4 (Development/Test)

### 6.1 Initiation Criteria

Tier 4 failover is discretionary and initiated only when:
• Extended outage projected >72 hours
• Development team requests DR activation for testing continuity
• Pre-scheduled DR test exercise

### 6.2 Execution Steps

1. Assess business need for DR activation (varies)

2. Restore development environments from daily backup (120-240 min)

3. Validate basic connectivity and application functionality (60 min)

4. Notify development teams of environment availability (15 min)

## 7. Communication and Escalation Plan

The DR communication plan follows a tiered notification structure. All notifications are tracked in the incident management system (ServiceNow) and logged for regulatory audit.

## 8. DR Test Results and History

The following table summarizes all DR tests conducted in the past 24 months. FINRA Rule 4370 requires annual testing with documented results.

Status: The most recent successful full Tier 1 failover test (DR-TEST-023) was conducted on June 15, 2023. The scheduled October 2024 Tier 1 test (DR-TEST-030) was postponed due to resource conflicts with the data center migration planning initiative. A replacement test date has not yet been scheduled.

Compliance Note: FINRA Rule 4370 requires documented testing of business continuity plans at least annually. As of October 2024, Meridian's last successful full Tier 1 test is 16 months old, placing the firm at risk of a regulatory finding during the next examination cycle.

## 9. Dependency Chain Analysis

Critical path analysis for DR recovery identifies the following dependency chains. Each chain represents a sequence of workloads that must be recovered in order, with the total chain recovery time determining the effective RTO for end-to-end service restoration.

The critical path for end-to-end recovery is Chain DC-4 (Regulatory Reporting) at 2h 30m, which exceeds the Tier 1 RTO target of 2 hours. This gap has been escalated to the Business Continuity Committee and is pending architectural remediation.

## 10. Recovery Site Specifications

Currently, Facility B (Stamford) serves as the primary DR site for Facility A (Newark), and vice versa. This mutual DR arrangement provides geographic separation of approximately 45 miles. Post-migration, the DR strategy will need to be redesigned based on the selected vendor's DR capabilities.

## 11. Data Replication Architecture

Data replication is implemented at multiple layers to provide defense-in-depth protection:

Total replication bandwidth requirement: 12.7 Gbps (peak concurrent). Available inter-facility bandwidth: 20 Gbps (2×10G). Effective available bandwidth after replication: 7.3 Gbps.

## Appendix A: Emergency Contact Directory

## Appendix B: Recovery Validation Checklists

### Tier 1 Recovery Validation

☐ Verify all Tier 1 VMs are powered on and responding to ping

☐ Confirm database replication status (zero lag)

☐ Validate trading system connectivity to exchange gateways

☐ Test order submission (paper trade) through full pipeline

☐ Verify market data feeds are active and current

☐ Confirm core banking transaction processing capability

☐ Test authentication services (AD, MFA) from DR site

☐ Validate network routing tables and BGP peering status

☐ Confirm DNS resolution for all Tier 1 service endpoints

☐ Verify monitoring and alerting systems are operational

☐ Test client VPN access through DR network path

☐ Confirm backup schedule is active at DR site

### Tier 2 Recovery Validation

☐ Verify all Tier 2 VMs are powered on and responding

☐ Validate risk analytics engine is processing feeds

☐ Test compliance reporting system end-to-end

☐ Verify client portal accessibility from external network

☐ Confirm settlement processing capability

☐ Test regulatory data submission workflow

### Tier 3 Recovery Validation

☐ Verify snapshot restore integrity (checksum validation)

☐ Confirm batch processing jobs are queued

☐ Test reporting database query capability

☐ Validate data warehouse refresh pipeline

### Tier 4 Recovery Validation

☐ Verify backup restore completed successfully

☐ Confirm development environment basic functionality

☐ Test source code repository access

## Appendix C: Regulatory Requirements for Disaster Recovery

## Appendix D: DR Performance Visualizations

Figure D.1: Historical DR Test Recovery Time Performance

Figure D.2: Inter-Facility Replication Bandwidth Utilization Profile

Figure D.3: Dependency Chain Recovery Times vs RTO Target

| Tier | Classification | RTO | RPO | Replication Method | Failover Mode | Test Frequency |
| --- | --- | --- | --- | --- | --- | --- |
| Tier 1 | Mission Critical (Trading, Core Banking) | 2 hours | 0 (synchronous) | Synchronous replication (Zerto + storage-level) | Automated failover with manual confirmation | Monthly |
| Tier 2 | Business Essential (Risk, Compliance, Client) | 4 hours | 15 minutes | Near-synchronous (RPO journal) | Semi-automated (scripted with approval) | Quarterly |
| Tier 3 | Standard Operations (Reporting, Analytics) | 24 hours | 4 hours | Asynchronous replication (snapshot-based) | Manual failover (documented procedure) | Semi-annually |
| Tier 4 | Development/Test (Non-production) | 72 hours | 24 hours | Daily backup (off-site copy) | Manual rebuild from backup | Annually |
| Unclassified | Workloads pending tier assignment | N/A | N/A | No replication configured | N/A | N/A |

| Sequence | Workload | Must Start After | Max Start Delay |
| --- | --- | --- | --- |
| 1 | WL-010 (Database Cluster) | Infrastructure Ready | 0 min |
| 2 | WL-005 (Message Queue) | WL-010 Active | 5 min |
| 3 | WL-001 (Core Banking) | WL-005, WL-010 Active | 10 min |
| 4 | WL-003 (Trading Engine) | WL-001, WL-010 Active | 5 min |
| 5 | WL-008 (Risk Engine) | WL-003 Active | 10 min |
| 6 | WL-012 (Client Portal) | WL-001 Active | 15 min |
| 7 | WL-002 (Settlement) | WL-001, WL-003 Active | 20 min |
| 8 | WL-015 (Compliance) | WL-001, WL-002 Active | 30 min |
| 9 | WL-004 (Reporting) | WL-001 Active | 45 min |
| 10 | WL-020 (Analytics) | WL-004, WL-008 Active | 60 min |

| Timeline | Audience | Method | Content |
| --- | --- | --- | --- |
| T+0 min | NOC / DR Coordinator | PagerDuty alert | Outage detected, assessment initiated |
| T+5 min | CIO, VP Operations, VP IT | SMS + Voice Bridge | Severity assessment, failover recommendation |
| T+15 min | Business Unit Heads | Email + Teams | Impact assessment, estimated recovery time |
| T+30 min | Compliance Officer | Email | Regulatory notification assessment |
| T+60 min | All affected staff | Email blast | Status update, workaround instructions |
| T+4 hours | FINRA / SEC (if required) | Formal filing | Regulatory notification per Rule 4370 |
| Post-recovery | All stakeholders | Formal report | Root cause analysis, lessons learned |

| Test Date | Test ID | Scope | Tier | Result | RTO Achieved | RPO Achieved |
| --- | --- | --- | --- | --- | --- | --- |
| 2023-06-15 | DR-TEST-023 | Full Tier 1 Failover | Tier 1 | PASS | 1h 48m (Target: 2h) | 0 min (Sync OK) |
| 2023-09-22 | DR-TEST-024 | Tier 2 Tabletop Exercise | Tier 2 | PASS | N/A (Tabletop) | N/A |
| 2023-12-10 | DR-TEST-025 | Storage Failover Only | Tier 1-3 | PARTIAL | 2h 15m (Exceeded 2h) | 3 min data gap |
| 2024-03-18 | DR-TEST-026 | Full Tier 2 Failover | Tier 2 | PASS | 3h 22m (Target: 4h) | 12 min (Target: 15m) |
| 2024-04-10 | DR-TEST-027 | Tier 1 Failover (Planned) | Tier 1 | CANCELLED | N/A | N/A |
| 2024-06-28 | DR-TEST-028 | Tier 3 Restore from Backup | Tier 3 | PASS | 18h 45m (Target: 24h) | 3h 12m (Target: 4h) |
| 2024-08-15 | DR-TEST-029 | Network Failover Only | All | PASS | 45 min | 0 min |
| 2024-10-05 | DR-TEST-030 | Tier 1 Failover (Rescheduled) | Tier 1 | POSTPONED | N/A | N/A |

| Chain ID | Chain Name | Workloads (in order) | Total Chain RTO | Critical Path? |
| --- | --- | --- | --- | --- |
| DC-1 | Trading Execution | WL-010 → WL-005 → WL-001 → WL-003 → WL-008 | 1h 45m | YES |
| DC-2 | Client Services | WL-010 → WL-001 → WL-012 → WL-006 | 1h 30m | NO |
| DC-3 | Settlement Processing | WL-010 → WL-001 → WL-002 → WL-015 | 2h 05m | YES |
| DC-4 | Regulatory Reporting | WL-010 → WL-001 → WL-004 → WL-015 → WL-020 | 2h 30m | YES |
| DC-5 | Risk & Analytics | WL-010 → WL-003 → WL-008 → WL-020 → WL-025 | 2h 15m | NO |

| Specification | Facility A (Newark) | Facility B (Stamford) |
| --- | --- | --- |
| Total IT Power Capacity | 2,500 kW | 1,800 kW |
| Current IT Load | 1,847 kW | 925 kW |
| Available DR Headroom | 653 kW | 875 kW |
| DR Compute Allocation | 32 servers (reserved) | 28 servers (reserved) |
| DR Storage Allocation | 120 TB (replicated) | 85 TB (replicated) |
| Inter-facility Bandwidth | 2×10G DWDM (20 Gbps) | 2×10G DWDM (20 Gbps) |
| Replication Lag (Tier 1) | <1 second (sync) | <1 second (sync) |
| Replication Lag (Tier 2) | <15 minutes (near-sync) | <15 minutes (near-sync) |
| Replication Lag (Tier 3) | 4 hours (async snapshot) | 4 hours (async snapshot) |
| Last Replication Audit | 2024-08-15 | 2024-07-22 |

| Layer | Technology | Scope | RPO Capability | Bandwidth Required |
| --- | --- | --- | --- | --- |
| Hypervisor | Zerto 9.5 | VM-level replication (Tier 1-2) | Seconds (journal-based) | 3.2 Gbps (sustained) |
| Storage | NetApp SnapMirror | Volume-level replication (all SANs) | 15 min (schedule-based) | 2.1 Gbps (burst) |
| Database | Oracle Data Guard | Database-level (Oracle workloads) | 0 (sync redo shipping) | 1.8 Gbps (peak) |
| Database | SQL Server AlwaysOn | Database-level (MSSQL workloads) | 0 (sync commit) | 0.9 Gbps (peak) |
| Application | Custom SFTP sync | File-level replication (reports) | 1 hour | 0.2 Gbps (scheduled) |
| Backup | Veeam B&R 12 | Full VM backup (all tiers) | 24 hours (daily) | 4.5 Gbps (window) |

| Role | Primary | Phone | Backup | Escalation |
| --- | --- | --- | --- | --- |
| DR Coordinator | J. Thornton | 201-555-0101 | R. Chen | M. Torres (CIO) |
| Network Lead | R. Chen | 201-555-0102 | K. Park | J. Thornton |
| Storage Lead | K. Anderson | 201-555-0103 | S. Davis | J. Thornton |
| Application Lead | P. Garcia | 201-555-0104 | L. Martinez | J. Thornton |
| Security Lead | T. Nakamura | 201-555-0105 | A. Singh | M. Torres |
| Compliance Officer | M. Williams | 201-555-0106 | D. Brown | General Counsel |
| CIO | M. Torres | 201-555-0110 | S. Chen (VP) | CEO |
| VP Operations | S. Chen | 201-555-0111 | J. Thornton | M. Torres |
| CFO | D. Park | 201-555-0120 | Deputy CFO | CEO |
| General Counsel | L. Torres | 201-555-0130 | Outside Counsel | CEO |
| Facility Manager (NWK) | B. Harrison | 201-555-0140 | Shift Supervisor | J. Thornton |
| Facility Manager (STM) | C. Reeves | 203-555-0140 | Shift Supervisor | J. Thornton |
| NOC (24x7) | Duty Manager | 201-555-0200 | N/A | J. Thornton |
| Vendor A Emergency | M. Webb | 201-555-8400 | NOC | Account Manager |
| Vendor B Emergency | NovaBridge NOC | 732-555-7700 | N/A | Account Manager |

| Regulation | Requirement | Meridian Status | Last Audit |
| --- | --- | --- | --- |
| FINRA Rule 4370 | Annual BCP review and testing | Testing overdue (last: Jun 2023) | May 2024 |
| SEC Rule 17a-4 | Records retention and accessibility | Compliant | Aug 2024 |
| OCC 2019-58 | Third-party risk management | Under review (migration) | Mar 2024 |
| SOX Section 404 | IT general controls over financial reporting | Compliant | Jul 2024 |
| PCI-DSS v4.0 Req 12.10 | Incident response plan testing | Compliant | Sep 2024 |
| HIPAA Security Rule | Contingency plan (addressable) | Compliant | Jun 2024 |